# Giving Tuesday 2025 — Campaign Brief

# 1) Overview

Giving Tuesday is a global day of generosity on the Tuesday after Thanksgiving. This campaign focuses on mobilizing current donors and engaged prospects to make a gift and share our mission.

# 2) Objective

Primary: Raise $550,000 in 24 hours while acquiring 2,500 new donors.

Secondary: Drive social shares and peer-to-peer referrals to expand reach.

# 3) Audience

Active donors (last 24 months), lapsed 24–48 months, email subscribers, and social followers.

Lookalike audiences built from recent donor and website engagement signals (no PII exported).

# 4) Value Proposition & Message Pillars

Impact-first: “Your gift today powers relief where it’s needed most.”

Urgency: “One day. One goal. Thousands helped.”

Trust & transparency: clear use-of-funds and outcomes.

# 5) Offer & CTA

Core offer: Unrestricted gift matched 1:1 up to $150,000 by a corporate partner (pending).

Primary CTA: Give now

Secondary CTA: Share the campaign link with 3 friends.

# 6) Channels & Tactics

Email cadence: teaser (T‑3), launch (morning), reminder (late afternoon), final push (evening).

Social: 4 organic posts (Mon night teaser; Tue morning launch; Tue noon impact; Tue 8pm final push).

Paid: social + search retargeting; tighten geography and intent keywords on the day.

Site: homepage hero banner + lightweight landing page with progress bar and mobile‑first donate flow.

# 7) Content & Assets

Hero image (1200×628), 1 short video (≤15s), 4 square social tiles, 3 email banners, 1 progress bar module.

Copy variants: 3 subject lines per send; short/medium/long body text; social captions (≤120 chars).

Accessibility: alt text for all images; color contrast AA+; keyboard focus on donate buttons.

# 8) Timeline

| Phase | Dates (2025) | Deliverables |
| --- | --- | --- |
| Prep | Nov 10–24 | Assets finalized; QA email + landing page; schedule paid; publish teaser |
| Launch Day | Dec 2 (Giving Tuesday) | 3–4 emails; 4 social posts; progress updates; donor thank‑you |
| Follow‑up | Dec 3–10 | Receipt + impact thank‑you; final totals; new donor welcome series |

# 9) Budget (rough)

Paid media: $50,000 (social + search).

Creative & production: $8,000.

Email & marketing ops: in‑house.

# 10) KPIs & Targets

Revenue: $550,000; New donors: 2,500; Average gift: $85.

Email CTR ≥ 6%; Landing→Donation conversion ≥ 6%.

ROAS ≥ 4.0 across paid media.

# 11) Risks & Mitigations

Match not confirmed → Plan B messaging without match; adjust revenue target by –15%.

Site latency under peak load → Pre-warm cache; simplify page; add status page link.

Inbox competition → Subject line testing; stagger send times; use strong preheaders.

# 12) Governance & Compliance

No export or sharing of PII outside tenant systems. Do not paste donor data into chat.

Use brand style guide; ensure accessibility (WCAG 2.1 AA).

Legal review for match language and tax statements by Comms lead.

# 13) Approvals

Owner: Marketing Operations Lead
Approvers: Creative Director, Development Director, MarCom Lead

# Links

SharePoint folder: /Marketing/Campaigns/GivingTuesday2025/